## Slide 1
PROJECT PLAN

## Slide 2
PROJECT'S MODEL
EARLY DESIGN
WHY:
  New service
  No pre-existent requirement
  No legacy software/hardware

## Slide 3
ROADMAP
ROAD TO EFFORT & DURATION ESTIMATION
  Intermediate stop
SCHEDULING & RESOURCES ALLOCATION
RISKS MANAGEMENT

## Slide 4
EFFORT & DURATION ESTIMATION
ESTIMATION MEAN
  COCOMO II model
THE MODEL
  MAIN EFFORT EQUATION:
    here
  DURATION EQUATION:
    here
HOW TO USE
  EVALUATE PROJECT'S SIZE
  ANALYZE PROJECT'S SCALE FACTORS
  ANALYZE PROJECT'S COST DRIVERS

## Slide 5
INTERMEDIATE STOP
INTERMEDIATE PROCEDURE: FUNCTION POINTS
THE MODEL:
HOW TO USE
  EVALUATE PFP OF
    INTERNAL LOGIC FILES
    EXTERNAL INTERFACE FILES
    EXTERNAL INPUTS
    EXTERNAL INQUIRES
    EXTERNAL OUTPUTS
SIZE ESTIMATION

## Slide 6
EFFORT & DURATION ESTIMATION
SIZE ESTIMATION
  UFP = 196
  KSLOC = 10.192 – 12.544
EFFORT ESTIMATION
92 - 114 persons/month
DURATION ESTIMATION
15.23 – 16.34 months
NB: UFP → KSLOC gearing factor computed as average between JEE’s and .NET’s gearing factors.

## Slide 7
RISKS MANAGEMENT
PROJECT RISKS
TECHNICAL RISKS
BUSINESS RISKS

## Slide 8: PROJECT RISKS
PROJECT REQUIREMENTS CHANGES
TECHNOLOGY INEXPERIENCE
UNREALISTIC DEADLINE
STAFF ISSUES

## Slide 9: TECHNICAL RISKS
SOURCE CODE LOOSE
CLOUD INFRASTRUCTURE UNAVAILABILITY
OBFUSCATED CODE
EXTERNAL RESOURCES DELIVERY DELAY
EXTERNAL SERVICES CHANGES

## Slide 10: BUSINESS RISKS
INTERNAL BANKRUPTCY
EXTERNAL SUPPLIERS BANKRUPTCY
LAW CHANGES